| Agenda Item | 9.1 |
| --- | --- |
| Subject | Westfield Down Update |
| Author | Proper Officer |
| Date | 19/02/2024 |

# Overview

- The following paper is to update Cllrs on the position of the handover of the Recreational Land including the Football pitch and changing rooms

# Rother Rescinds Certificate of Satisfaction

- Despite numerous requests to Rother by the 22/01/2024 there was still no formal reply from officers in relation to any of the concerns raised by the Parish Council back in November 2023.  Another email was sent to the officers at Rother and then an email was sent to the Chief Executive outlining that due to Rother officer’s constant lack of engagement the Parish Council had no choice but to start the dispute process.  It was highlighted that “the Parish Council does not want to go down the dispute process as this will incur a cost and will further delay the handover of the land.  The Parish Council wanted to discuss this amicably before the Certificate was issued.  These concerns were ignored.”

- The Parish Council’s insurers Zurich were then contacted to get their position on the condition of the land and they replied:

  - The land that is being proposed for adoption appears to be presenting multiple hazards that would significantly increase the risk of a public liability incident occurring.

  - Until such time as the land can be made safe for public use, the land should be appropriately cordoned or segregated with public notice given to alert third parties to the hazards.

  - The land should not be open to the public until the hazards that have been presented have been adequately removed e.g. building debris removed and hazardous ground made safe.

  - The adoption of the land should only take place once an appropriate inspection of the land has been conducted.

- The Chief Executive and officers where sent the report from Bourne and the feedback from the Zurich.  The Chief Executive responded on the 26/01/2024 with the following:

  - Further to my recent email regarding the Westfield Down site and Certificate of Satisfaction, I can advise that as there are remedial works outstanding that cannot be completed at this time of year due to ground conditions, the Certificate of Satisfaction dated 1st December 2023 has been rescinded by the Council.  We have been advised by our Legal Department that as the Certificate was prematurely issued it is not valid and has no effect.

  - Moving forward, and in terms of the timeframe for carrying out the remedial works identified by the Council, the intention is for these works to be completed by Southern over the next few months with the new grass seed likely to be sowed in April (dependent on growing conditions). Once the remedial works have been completed by Southern, the Recreational Land will be re-inspected by the Council to ensure the defects have been rectified. Rother District Council will only issue the Certificate of Satisfaction once the defects which have been identified have been rectified and the Recreational Works have been completed to the Council’s satisfaction in accordance with the terms of the S106 Agreement dated 9th May 2014.  As you are aware Southern has within two months of the issue of the Certificate of Satisfaction to transfer their interests in the Recreational Land to the Parish Council.  This period does not commence until the Certificate of Satisfaction is issued.

  - Please be assured that Rother District Council would not want the Parish Council to take ownership of the Recreational Land until the Recreational Works have been fully completed to the reasonable satisfaction of the Local Planning Authority.  I would be grateful if you would confirm whether you still wish to start the dispute process in light of the above.  Para 15 of Part 2 of Schedule 3 of the S106 Agreement states that the “Owner (at its own cost) shall be responsible for maintaining the Recreational Land in a satisfactory condition until the date of transfer of the Recreational Land to the Parish Council.”  Should Southern fail to maintain the Recreational Land in a satisfactory condition they will be in breach of the S106 Agreement.

- A reply was also promised within a couple of weeks from the Director of Place and Climate and to contact him if there were any further questions.  A question was raised why none of these concerns have been dealt with or considered before the Certificate of Satisfaction was issued but no reply was received.

- A further email has been sent on the 19/02/2024 requesting a date for a reply from Rother.

- It has been highlighted in nearly every email that the Parish Council does not consider a ‘pick’ suitable enough to make the site safe for it’s end use.  This is following the advice of Bourne and confirmation from the insurers that the Parish Council would be held liable if anyone hurt themselves on site because the risks were known to the Parish Council.

- Rother have been asked again to confirm if they are only asking Southern Housing to carry out with the ‘pick’ or if the top 200mm of soil will be properly screened and cleared.  Rother have also been asked to confirm the specification they are working to in relation to the recreational area.

# Ongoing Concerns to the Potential Reissuing of the Certificate of Satisfaction

- Rother have been notified that moving the Parish Council still have a number of concerns and questions which remain unanswered even with the rescinding of the Certificate of Satisfaction which were outlined as below:

- Who have Rother used as their suitably qualified consultant for the spec and proposed works for all the Recreational Works in relation to building out the recreational land being proposed to be handed over to the Parish Council.  There is a requirement in the s106 para 1.1, part 1 of the seventh schedule for qualified consultants to “advise and assist the Local Planning Authority in discharging the responsibilities in paragraphs 2 and 3 of this Part 2 of the Seventh Schedule”.  The Parish Council has requested visibility of the aforementioned specialist advice/report. Bourne who are qualified professionals do not think the site is suitable and have noted the works will not be completed for 12 months from the original brief from Rural Ground Contracts Ltd.

- The only documentation the Parish Council has seen outlining any specification for the land is on the Rother planning portal titled “Amended Grading and Seeding Works – Technical Specification” submitted by Rural Ground Contracts Ltd.  However, Bourne have commented on this specification and concerns from the Parish Council have been highlighted below:

  - Due to the significantly high levels now on site, have the District Council confirmed that all the soil is from the existing site?  Please note in para 13 the Chief Executive of Southern Housing has confirmed that all soil on site is from site and clean and inert.

  - It would appear that the top and sub soil have indeed mixed in numerous areas which Bourne note creates establishment problems for grass.

  - Whilst the rescinded Certificate of Satisfaction notes reseeding should happen in April 2024 if the soil is such poor quality there are issues if grass cannot establish and be used for its intended use as Recreation Land.

  - Has a topographical survey been carried out on the finished area (as built plan) and compared with the “levels plan”.

  - In many areas there is now no top soil that can be seen as it has been washed away.  Nothing in the rescinded Certificate of Satisfaction addresses these issues or suggest a minimum level of top soil across the site not just in areas to deal with trying to disperse the issue of standing water on site.

  - Was the soil screened for the 75mm as on site many items have been found over this size and is a very big concern for the Parish Council.  The intended end use and description of this site is for recreational land.  Bourne have identified that the soil does not appear to have been screened but also question whether the 75mm is even suitable considering the end intended use and quote stones of 32mm should only be present in the top 200mm of the rootzone.  Westfield Parish Council request visibility of the specialist consultant’s advice/report that would satisfy the Parish Council’s insurers that the land will be made safe and remove the risks and therefore the liability to the Parish Council.

  - Could Rother confirm who is engaged in carrying out these remedial works?

  - Reassurance that before any Certificate of Satisfaction is signed any potential issues with the water contamination for Spring and Autum Cottages are dealt with fully.

  - As the Certificate of Satisfaction has now been rescinded with the variation to the s106 para 12.1 part two of the third schedule states “Not to allow occupation of more than 14 of the Shared Ownership Dwellings included in the Planning Permission unless the Recreational Works shall have been fully completed to the reasonable satisfaction of the Council (having regard to any reasonable advice which may be provided by the Football Association) and the Council shall have provided the Owner with a Certificate of Satisfaction to that effect.” If any of the shared ownership properties have been sold Southern Housing would have done this having received the Certificate of Satisfaction.  However, as per the s106 no further shared ownership properties should be sold from the date the Certificate of Satisfaction has been rescinded.  Please can Rother or Southern Housing confirm this.

# Geo-mapping and Soil Testing of the Site

- Southern have been contacted to confirm they are happy for these works to be carried out.  The Chief Executive of Southern Housing has confirmed that any non-evasive works can be carried out.

- The Chief Executive has confirmed that “The material underneath the pitch is from when the site was stripped as per the planning approved method statement and therefore clean and inert.”

- Any ‘invasive’ methods they will only allow once they have completed the remedial works and Rother has reinspected.  This is to stop any potential delay in the Certificate of Satisfaction being delayed and / or their Contractor disputing remedial works.

- Both tests will have to be at the cost of the Parish Council and all findings will be shared with Southern Housing.

# The Use of the Football Pitch and Changing Rooms

- During a site visit with Southern Housing it was requested that Southern Housing look at giving Westfield FC a license to use the football facilities.  Happily Southern have agreed to this allowing WFC to use and maintain the site.

- After discussions with WFC it has been suggested that any long term or permanent changes are also agreed with the Parish Council who will ultimately be the end landlords of the site.

# The Legal Process for Transferring the Land

- Whilst the matter of the Certificate of Satisfaction continues legal representation has been sought to manage the legal process of handing over and registering the land to the Parish Council.  The suggested solicitors are a local company Herringtons.

- A solicitor will need to oversee the following matters:

  - The transfer of the land from Southern Housing to Westfield Parish Council.  The land is actually held currently by Optivo not Southern Housing so the solicitor will look into this matter.  The solicitor will also need to ensure the wording and transfer of land takes into account any potential future names changes of Southern Housing.

  - The transfer of a lease of the land from the Parish Council to Westfield Football Club and the accompanying lease which has already been drawn up.  WFC have been informed that they will need legal representation in this matter.

# Resolutions for Council

- Cllrs to note this response and the correspondence with Rother District Council.

- To confirm all concerns from the Parish Council have been covered by those outlined in paragraphs 9 to 11.

- Councillors to confirm if they wish to continue with the formal ‘dispute process’ if Rother do not intend for a proper cleaning of the soil in the top 200mm as recommended by Bourne and stick to only requesting a ‘pick’ on site.  If Cllrs do wish to start the dispute to delegate authority to the Proper Officer to carry out this process.

- To resolve to carry out the geo-mapping and soil testing in accordance with Southern Housing conditions.  Funds to be taken out of EMR – Westfield Down.  Delegate Authority to the Proper Officer.

- Delegate Authority to the Proper Officer to oversee the legal process with Herringtons solicitors for the transfer of the land.  Funds to be taken out of EMR – Legal Fees.

- In any matters delegated to the Proper Officer she will ensure to find best value/quality in line with financial regs and consultation with the Open Spaces Working Group and Chairman.  Any expenditure will not exceed the funds held in the identified EMR.