| Agenda Item | 9.6 |
| --- | --- |
| Subject | Proposal to Start Neighbourhood Plan work |
| Author | Proper Officer |
| Date | 03/03/2025 |

# Overview

- In July 2024 the Parish Council resolved to move forward with a Neighbourhood Plan (NP).  The Officer has worked since that time trying to ascertain the right time to start the NP in line with the current position of the Rother Local Plan.  This paper is intended to give a proposal to start developing plans and scoping exercises to enable the development of potential options to take this matter forward.

- To date it has been difficult to understand form Rother District Council (RDC) what their

# Key Proposal

- The key proposal for starting the Neighbourhood Plan focuses on two key action points:

  - Develop an outline project management plan (attached in appendix one).

  - Work with an established Neighbourhood Plan consultant ONH to develop the next steps.

# Brief Introduction to ONH

- Over the last decade ONH have become the market leader in terms of providing town and parish councils and neighbourhood forums with independent professional support for their neighbourhood plan projects. We have now supported over 200 new, modified and replacement neighbourhood plan projects across 60 planning authority areas. They also provide a range of planning and asset management services to town and parish councils, ranging from design coding, commenting on major planning applications and draft Local Plans, to representing them at planning committees, appeals and Local Plan inquiries.

# Scope of Work

- The proposed scope of work is divided into two parts, with the first would be at a cost of £3,625.  The aim would be to have the Parish Council complete this stage in the next couple of months so the second can be scoped and agreed.

- Part One will consist of the follow elements:

  - Carry out a review of the adopted and emerging Local Plans (and their evidence bases), relevant ESCC policy, the High Weald Management Plan and a selection of key planning applications.

  - Meet (online) with Parish Councillors and the Clerk to discuss governance and management options and constraints.

  - Prepare a slide pack of key insights

  - Arrange and host a 2 – 3 hour, in-person session with councillors to present the slide pack and to debate its insights.

  - Produce a summary note of the session that sets out an appraisal of the options for the Parish Council to consider taking the Neighbourhood Plan forward.

- Once Part One has been carried out it would give the Council the option to consider what elements they would like to include in the second part of the work.

- Part Two (not included in this current payment) would be defined once the Parish Council has considered the summary produced in Part One and agreed what external support it requires to complete the project.

- An overview of what the scope for Part Two may comprise ONH are able to offer the following support:

  - Additional evidence gathering and analysis and/or briefing and managing Locality technical support package contractors to deliver quality reports on time

  - Site assessment process operation

  - Drafting policy wording and supporting text

  - Producing the plan document, including GIS-based policy maps

  - Health checking final pre-submission documentation before approval

  - Advice and guidance on consultation strategy

  - Reviewing comments made by the LPA and statutory bodies during the presubmission consultation period and making recommendations for key modifications

  - Revising policy wording, supporting text and policy maps as instructed

  - Producing the Basic Conditions Statement

  - Reviewing the Consultation Statement produced by the client

  - Health checking final submission documentation before approval

  - Reviewing comments made during the pre-examination publicity period and helping answer examiner queries

# Resolutions for Council

- Councillors to RESOLVE the fee and support from ONH at £3,625.

- Councillors to RESOLVE the outline Project Plan

# Appendix One – Draft NP Project Plan

- Main Objective:

  - To create a complete and comprehensive Neighbourhood Plan for the whole area known as Westfield Parish Council. a specific UK parish, following government guidelines and ensuring local community participation, addressing housing, environment, transport, economy, and infrastructure.

- Phase 1: Preparation & Initial Engagement

  - Define the Scope and Objectives of the Neighbourhood Plan.

  - Identify resources and funding to be identified along with necessary resources, including funding options (e.g., grants from the government or other bodies) and consultant fees.

  - Identify key themes and priorities for the parish (e.g., housing, design, allocation of sites, traffic, dark skies, biodiversity)

  - Set out the plan’s core purpose and intended outcomes.

  - Identify the role of the Officer of the Council, Parish Council leads and role of Consultant.

  - Establish a Steering Group with local residents, community leaders, parish council members, and experts.  Explore local partnerships e.g. with community groups, environmental organisations that could also feed into or be on the Steering Group.

  - Assign roles and responsibilities within the steering group.  Agree terms of reference to be approved by Parish Council at Full Council.

  - Schedule regular meetings to be minuted and give monthly progress reports back to Full Council.

  - Confirm legal framework through working with consultant and local planning authority (Rother District Council) to ensure compliance with current planning laws and local policies.

  - Register the parish with the local authority to create a formal Neighbourhood Plan Area which must be consulted on with parishioners.

  - Develop a communication plan identifying core communication outlets including a website, social media presence, and email newsletter for ongoing communication with the community along with a regular presence in the WOW newsletter.  This is to be done alongside a community engagement strategy identifying suitable times for public consultations, surveys, and events.

  - Organise a "Launch Event" to introduce the project and outline key objectives and timescales.  The promoted timescale will outline dates when surveys will be conducted and informal meetings to gather initial views from the community on the key issues that should be included in the plan.

- Phase 2: Data Collection & Analysis

  - Establish data gathering methods. Collect existing data related to the parish (e.g., population demographics, land use, transport patterns, local economy).  Commission studies or surveys to gather additional data if necessary (e.g., housing needs assessment, traffic studies).

  - Identify potential sites to allocate for development, considering various land uses such as housing, employment, community facilities, and infrastructure.  Ensure that any sites proposed for allocation meet national and local planning policies.

  - Conduct a site assessments (including environmental impact assessments, access to transport, local infrastructure capacity, and flood risk).  Engage with any relevant statutory consultees.

  - Conduct a SWOT (Strengths, Weaknesses, Opportunities, Threats) analysis for the parish to identify the key challenges and opportunities.

  - Meet with key stakeholders such as local businesses, education providers, healthcare providers, and environmental groups to gather their input.

  - Hold community workshops, drop-in sessions, and meetings with local stakeholders to gather feedback on potential sites and draft policies.  Ensure residents are provided with a range of ways to review the site proposals to review, comment on, and suggest alternative sites for consideration.

- Phase 3: Drafting the Neighbourhood Plan

  - Develop sessions to create a core vision and agree/identify objectives.  The vision statement should encapsulate the community's aspirations whilst the strategic objectives should be based on the community's needs and preferences gathered during consultations.

  - Start to develop outline core policies under themes such as housing, design and  environment.  Below are an idea of some potential headings and areas to review:

    - Site allocation would be an important and key part of the plan.  The figure of housing would come from the local planning authority but the aim would for the community through the NP to identify suitable sites for that housing.

    - Housing need should be established via Rother’s housing register but also from an independent housing need assessment.  This should address affordable housing need, types of housing size and suitable locations for development.

    - Environmental policies should be considered for sustainability, protecting green spaces, protecting darks skies, avoiding development creep, impact on the High Weald National Landscape and enhancing biodiversity.

    - Transport matters should reflect core concerns identified in the 2019 consultation process and review these for any other key traffic issues.  Focus on improving speeding issues across the parish.

    - Economy policies to be developed to encourage local business development, protecting rural jobs and livelihoods, protecting existing employment sites and look at opportunities for economic diversification.

  - A draft the NP document will need to be prepared.  An example of sections to include:

    - Introduction

    - Vision and objectives

    - Background context and evidence

    - Detailed policies for land use, housing, transport, environment, and economy

    - Site allocations

    - Community aspirations and future goals

  - An important part of the Environmental Assessment

- Carry out a Sustainability Appraisal (SA) and Strategic Environmental Assessment (SEA) as required by UK regulations.

- Phase 4: Consultation on the Draft Plan

  - Public Consultation – Present the draft Neighbourhood Plan to the community for review and feedback. Host public meetings, workshops, and drop-in sessions.

  - Distribute a formal consultation document, allowing for online and paper feedback.

  - Review feedback received from consultations and make amendments to the plan where necessary.  Ensure any changes are in line with the original vision and community aspirations.

  - Pre-Submission Consultation (Regulation 14) – Undertake the formal pre-submission consultation required by the Localism Act 2011 (Regulation 14).

  - Notify the local planning authority and consult statutory bodies such as Natural England, Historic England, and the Environment Agency.

- Phase 5: Submission & Examination

  - Finalise the Neighbourhood Plan ensuring all revisions and consultations have been incorporated.

  - Complete any final legal documentation required for submission.

  - Submit the completed Neighbourhood Plan to the local planning authority for review and formal consultation.

  - Independent Examination requires the Local Authority will appoint an independent examiner to review the Neighbourhood Plan for compliance with regulations, consistency with local planning policies, and the broader legal framework.

  - The examiner may recommend modifications to the plan before it can proceed.

- Phase 6: Referendum & Adoption

  - Community Referendum can happen if the independent examiner approves the plan, the local authority will organize a local referendum for residents to vote on the plan.

  - Ensure that the community is informed and encouraged to participate in the referendum.

  - Adoption of the Neighbourhood Plan can take place if the majority of voters approve the plan (over 50%), the Neighbourhood Plan will be officially adopted.

  - The plan will become a part of the statutory planning framework and will guide local development decisions.

- Phase 7: Post-Adoption Monitoring & Review

  - Monitor the implementation of the Neighbourhood Plan’s policies.

  - Ensure that the development and planning applications align with the plan’s policies.

  - Regularly review the plan (typically every 5 years) to ensure it remains relevant and up to date with changing circumstances, policy updates, and new community needs.

  - Amend the plan as necessary in response to significant changes (e.g., new government policies, local economic shifts).

- Potential Timeline Summary

  - Phase 1 (Preparation & Initial Engagement): 2-3 months

  - Phase 2 (Data Collection & Analysis): 3-6 months

  - Phase 3 (Drafting the Neighbourhood Plan): 4-6 months

  - Phase 4 (Consultation on the Draft Plan): 2-3 months

  - Phase 5 (Submission & Examination): 3-4 months

  - Phase 6 (Referendum & Adoption): 2 months

  - Phase 7 (Post-Adoption Monitoring & Review): Ongoing (every 5 years)