| Agenda Item | XXX |
| --- | --- |
| Subject | Budget Monitoring Report 2025-26 |
| Author | Finance Working Party and Responsible Financial Officer |
| Date | 13/11/2025 |

Introduction

- This report provides a full line-by-line analysis of the Revenue & Payments (R&P) sheet for the 2025–26 financial year to date.
It includes:

  - Actual income and expenditure recorded

  - Approved budget figures

  - Forecast end-of-year (EOY) projections

  - Variance analysis and commentary

  - Identification of discrepancies and areas requiring action

Income Lines – Line-by-Line Review

- 1000 – Hirings

  - Actual: £0

  - Budget: £0

  - Forecast: £0

  - Hirings have generated no revenue.

- 1005 – Grants

  - Actual: £26,226

  - Budget: £0

  - Forecast: £26,226

  - Positive variance: +£26,226

  - This represents unbudgeted grant income from the Rother Community Grant Scheme as this was not guaranteed income it was not included in the main budget.  Council to consider if future budgets optimistically put in potential grants.  Concern is this may give a false position on projects.  Recommendation to not include grants unless guaranteed.

- 1006 – Miscellaneous Receipts

  - Actual: £0

  - Budget: £0

  - Forecast: £0

  - No miscellaneous income received.

- 1076 – Precept

  - Actual: £118,770

  - Budget: £118,770

  - Forecast: £118,770

  - No variance.

- 1100 – CiL (Community Infrastructure Levy

  - Actual: £1,642.68

  - Budget: £0

  - Forecast: £1,642.68

  - No variance.

  - CiL cannot be budgeted for.  The Parish Council can receive up to 15% of any CiL obtained on sites within the Parish.  However, the Parish Council cannot not budget for this income as it is not guaranteed.  Even with planning permission granted the CiL is only passed onto the Parish Council once building has commenced or sometimes when completed.

- 105 – VAT Repayment

  - Actual: £0

  - Budget: £22,113.98

  - Forecast: £22,113.98

  - No variance.

  - Due to the large VAT expenditure this year the RFO will be making a 6 month VAT claim to put the funds back into the accounts.

- Income Total

  - Actual: £146,638.68

  - Budget: £140,883.98

  - Forecast: £167,109.98

  - Variance (Actual–Budget): +£5,754.68

  - Variance (Forecast–Budget): +£27,868.68

  - Explanation: Entire positive variance is due to unbudgeted grant and CiL income.

Expenditure Lines – Line-by-Line Review

- Admin Expenditure Total

  - Budget: £70,514.85

  - Actual to date: £39,512.13

  - Forecast EOY: £72,828.53

  - Variance (Actual vs Budget): –£31,002.72 (underspend to date / favourable)

  - Variance (Forecast vs Budget): +£2,313.68 (slight forecast overspend)

  - Commentary: Spending is currently well below the annual budget, but the forecast suggests a small overspend by year-end. Worth checking what is still committed but not yet invoiced (e.g. salaries, contracts, support services).

- Open Spaces Income Total

  - Budget: £4,160.00

  - Actual to date: £200.00

  - Forecast EOY: £3,160.00

  - Variance (Actual vs Budget): –£3,960.00 (unfavourable)

  - Variance (Forecast vs Budget): –£1,000.00 (unfavourable)

  - Open Spaces income is behind target, and even the year-end forecast is £1,000 below budget. This is because the Westfield Down has not been handed over so the football club’s £1,000 annual rent for the ground is unlikely to be collected this year.

- Open Spaces Expenditure Total

  - Budget: £26,450.00

  - Actual to date: £73,453.90

  - Forecast EOY: £79,776.52

  - Variance (Actual vs Budget): +£47,003.90 (overspend)

  - Variance (Forecast vs Budget): +£53,326.52 (overspend)

  - Commentary: It is not an overspend as the expenditure was not in the budget but paid for via earmarked reserves £21,172 and the grant of £26,226 at a total of £47,398.

  - Recommendation: Transfer a further £5,400 of CiL funding to cover the remaining cost of the playground project.

- Grants Expenditure Total

  - Budget: £3,500.00

  - Actual to date: £0.00

  - Forecast EOY: £3,400.00

  - Variance (Actual vs Budget): –£3,500.00 (underspend to date / favourable)

  - Variance (Forecast vs Budget): –£100.00 (slight underspend forecast)

  - Commentary: £1,500 is allocated for the churchyard upkeep. £300 allocated for the RBL wreaths leaving another £1,600 towards any potential community grants.

- Projects Expenditure Total

  - Budget: £2,500.00

  - Actual to date: £3,357.03

  - Forecast EOY: £4,157.03

  - Variance (Actual vs Budget): +£857.03 (overspend)

  - Variance (Forecast vs Budget): +£1,657.03 (overspend)

  - Commentary: Projects are showing over budget but this is because the £3,125 from earmarked reserves has not been accounted for which pays for consultation for the Westfield Neighbourhood Plan project.

- Total VAT on Payments

  - Budget: £17,395.38

  - Actual to date: £14,415.84

  - Forecast EOY: £17,395.38

  - Variance (Actual vs Budget): –£2,979.54 (underspend to date)

  - Variance (Forecast vs Budget): £0.00

  - Commentary: VAT is on track overall, and the underspend to date is simply mirroring the timing and pattern of expenditure.

End of Year Summary

- Overall income is ahead of budget mainly due to unbudgeted grant income (£26,226).

- VAT repayment is budgeted but not yet received but this was submitted to HMRC w/c 10/11/2025 so should be received before end of the financial year.

- Admin expenditure is currently at an underspend around £31k and forecast is largely inline with the budget possibly a few £100 over at year end.

- Open Spaces Income is below budget (forecast shortfall of £1,000) as previously explained in paragraph 10.6.

- Expenditure largely above budget with an overspend £53k+.  However, as outlined in paragraph 11.6 this was a project and therefore not budgeted for but funding does in fact come from earmarked reserves and the grant which ahs already been received.  Recommendation to transfer CiL earmarked reserves to cover the remaining £5,400.

- Grants & Projects expenditure is not yet fully spent, small underspend expected.

- Projects: already over budget but because the £3,125 from earmarked reserves is not accounted for.

- VAT for this year is on target overall with no concerns.

Final Figures

- Total Actual Income – £146,638.68

- Total Actual Expenditure – £116,323.06

- Actual Expenditure from Earmarked Reserves – £27,397.00

- Forecast Income – £22,113.98

- Forecast Expenditure – £46,056.95

- Forecast Expenditure from Earmarked Reserves – £5,400

- Total End of Year Position to allocate to Earmarked Reserves – £65,776.08

Earmarked Reserves (EMR)

- This year there has been a total spend of £27,397.00 from EMRs.  That has included:

  - £3,125 – Neighbourhood Plan consultation fees

  - £1,900 – Parish realm improvements

  - £22,172 – Playground equipment replacement

  - £200 – Towards legal fees

- At the end of the year the final surplus is reviewed and allocated to the relevant EMRs.  Below is a table of the proposed increase which will only happen at the end of the year.

- With the Public Realm items this amount maybe less if some of the projects are completed 2025/26 which means the required EMR will also be less.

- Councillors are reminded to note that this paper needs to be considered in conjunction with the paper on the proposed projected increase on the precept 2026-2030.

- Along with the EMRs the Parish Council is also required to hold a minimum of 3 months budget running costs in core reserves.  For this year that sits at £20,721.84.  This leaves £45,776.08 remaining to allocated across the EMRs.  Below is a table outlining the proposed increases.

| Account | Est. Balance 31.03.25 | Proposed Increase | Proposed Decrease | Starting Balance 01.04.26 |
| --- | --- | --- | --- | --- |
| 311 Election Costs | £1,000.00 |  |  | £1,000.00 |
| 312 Playground Areas | £0.00 |  |  | £0.00 |
| 313 Public Realm Items | £2,492.63 | £13,000.00 |  | £15,492.63 |
| 314 Tennis Courts | £1,000.00 |  |  | £1,000.00 |
| 316 Cottage Lane Footpath | £0.00 |  |  | £0.00 |
| 317 War Memorial and VE Day | £200.00 |  |  | £200.00 |
| 318 Parish Field & play equip | £0.00 |  |  | £0.00 |
| 320 Parish Plan/NP | £1,113.25 |  |  | £1,113.25 |
| 321 Cricket Pavilion | £0.00 |  |  | £0.00 |
| 322 Covid-19 | £0.00 |  |  | £0.00 |
| 324 Bus Shelters/Noticeboards | £0.00 |  |  | £0.00 |
| 325 Village Website | £172.00 |  |  | £172.00 |
| 326 Traffic Project | £0.00 | £2,000.00 |  | £2,000.00 |
| 327 Environment | £0.00 | £2,000.00 |  | £2,000.00 |
| 328 Westfield Down | £13,030.00 |  |  | £13,030.00 |
| 329 Legal Fund | £4,114.67 |  |  | £4,114.67 |
| 330 CiL | £1,972.98 | £1,643.00 |  | £3,615.98 |
|  | £25,095.53 | £22,643.00 | £0.00 | £45,738.53 |

Conclusion

- This paper is a review of the income and expenditure to date.  There are no unforeseen expenditure items.  Income and expenditure is on target overall for the end of the year.  It is noted that there has been some significant outlays from the EMRs to get projects completed and this has been positively received by the community.

- Councillors are asked to review the Proposed Precept Increase paper and the outstanding Parish Maintenance Paper

- Councillors are asked to note this paper and to RESOLVE if they are happy with the proposed split of EMRs.